## Backlog
Daniel Ramsey
Importance | Sprint Date | Status | Project | Goal Date | Project Owner | Department | Done Date | Impediment
1001

## Sprint Template
Template Sprint Name |  |  | 20%
Sprint Starte Date: |  |  | Sprint Due Date: |  | Sprint Complete Date:
Importance | Status | Objective | Notes | Asign to | Department | Time Spent | Def of Done | Review Date | Complete Date
20%
Done

## Agent Onboarding
Agent Onboarding
Sprint Start Date: |  |  | Sprint Due Date: |  | Sprint Complete Date:
Importance | Status | Objective | Notes | Asign to | Department | Forms / Documents Needed | Days til Launch | Time Spent | Def of Done | Review Date | Complete Date
1000 |  | Team Leader to send email of notifying that New Agent is starting | provides start date, time |  | Operations |  |  |  | support is aware of new employee
995 |  | Put Agent info in CRM | Agent Onboarding: How To's: Adding an Agent into CRM |  | Support |  |  |  | CRM is updated with agent info
990 |  | Support starts onboarding process | Agent Onboarding Checklist |  | Support | Checklist form
988 |  | Support sends standard welcome email to new agent | Welcome email to agent |  | Support | 2017 1099 form |  |  | Welcome email with requested info is in out box
985 |  | Support looks up New Agent License number | Look up by name - get license number |  | Support
983 |  | If agent is still listed under old agency, check back to see when freed | Check back 2x a day and update agent each time |  | Support
981 |  | register license | Step by step guide in Onboarding folder in Drive |  | Support |  |  |  | Print out of added agent shows new agent name on list
980 |  | Notify MLS of new affiliate | Insert MLS contact |  | Support |  |  |  | Support confirms new agent has been added
978 |  | Create a New Agent folder for all documents | put all docs, signed contracts etc in here |  | Support
975 |  | Procure copy of RE license | Give to Team Leader for file in his office |  | Support |  |  |  | copy of RE license is in personnel file
970 |  | Procuer 2 New Agent Bios (4 line and 5 line) | Save example to show |  | Support |  |  |  | Bio's are in personnel file and with Agent Marketing
965 |  | Procure professional picture of New Agent for business card |  |  | Support |  |  |  | Picture has been sent to Agent Marketing
963 |  | Confirms New Agent has Smartphone |  |  | Support |  |  |  | Agent has let support know their phone type
960 |  | Confirm receipt of required docs | Onboarding Completed Required Documents |  | Support |  |  |  | All docs from welcome email have been received
955 |  | Confirm all docs have been saved to new agent folder |  |  | Support
950 |  | Send professional photo to Agent Marketing | Business cards, Agent Marketing materials and plaque |  | Support |  |  |  | Support confirms they have photo
945 |  | Send bio to Agent Marketing | Agent Marketing to hold for 30 days before updating |  | Support |  |  |  | Support confirms they have bio
930 |  | Make a keycard for new Agent |  |  | Support |  |  |  | Agent has new key in hand
925 |  | Create new email address |  |  | Support |  |  |  | email address is active
920 |  | IT set up |  |  | Support |  |  |  | remote access and drives are accessable
910 |  | Confirm IT set up complete and test usernames and passwords |  |  | Support |  |  |  | confirm access is working properly
898 |  | Print out temporary business cards | Have ready for new agent arrival on first day |  | Agent Marketing
897 |  | Document passwords and put in master password file |  |  | Support | Master password form
895 |  | Once Google Drive is complete input preset folders | templates for forms, scripts and dialogue |  | Support |  |  |  | Folders are in new agents drive
894 |  | Set-up Section in Agent Accountability Folder | Daily Accountability Updates |  | Operations |  |  |  | Daily Accountability Updates has field for new agent
890 |  | Add regular weekly meetings to google calendar | weekly Tuesday, Huddle, Prospecting Nights |  | Support |  |  |  | Meetings are on new agents calendar
875 |  | Add name to Mailbox Inbox |  |  | Support
860 |  | Start Orientation Binder | Binders located: |  | Support
850 |  | Create basic 30-60-90 day plan |  |  | Operations |  |  |  | 90 day plan has been laid out
840 |  | Plan first day/ weeks tasks | meetings / what you want accomplished |  | Operations
835 |  | Set up new agent phone ext |  |  | Support
830 |  | Update and distribute phone lists with New Agents contact |  |  | Support | Phone List |  |  | phone lists include new agent info and has been distributed
820 |  | Supply copy of updated phone lists for New Agent Orientation binder |  |  | Support | Phone List |  |  | Put new phone list in orientation binder
817 |  | Confirm Orientation binder has all necessary info | Personalized page, welcome pages, copy of confidentiality agr, Important Info sheet, updated phone list, password and log in sheet, payroll sheet example, listing email, inventory email, fair housing, DISC, perfect week example, flood map, orientation sheet, evaluation |  | Support
815 |  | Send email to CCC to add New Agent |  |  | Support
810 |  | Email team about New agent | New role and bio and contact info |  | Support |  |  |  | Agent email has been sent to team
780 |  | Set up meetings with critical people for New Agents first week |  |  | Operations
720 |  | Add to payroll | Payroll Instructions |  | Support | Payroll instructions |  |  | Payroll is set up to pay new agent
700 |  | Record overnight Voice Mail | add password to master password list |  | Support |  |  |  | New agents Voice Mail is set up
450 |  | Agent Smart Phone Integration with CRM and Mail |  |  | Support
420 |  | Give new key to office | location of keys |  | Support |  |  |  | Key is in new agents hand
415 |  | Have New Agent sign employment documents | Commission Agreements, Position Agreement and Confidentiality Agreements |  | Support |  |  |  | Docs have signature on them and are in Team Leader's possession
410 |  | Overview of databases, folder locations |  |  | Support
400 |  | Review job description | outline duties and expectations |  | Operations
390 |  | Introduce to all team members |  |  | Support
385 |  | Give brief tour of office area | Basic things incase they start before orientation |  | Operations
380 |  | Review personal office set up |  |  | Support
370 |  | Have New Agent record Voice Mail as per standard Voice Mail script |  |  | Operations
360 |  | Meet and discuss expectations | 30-60-90 day goals, responsibilities and annual perfomance review |  | Operations
350 |  | Review probationary period | Reiterate company statement, values and culture |  | Operations
340 |  | Confirm New Agent training meetings | Scripts, CRM, Role Playing, phone systems, telepro, MLS, daily activity record |  | Support |  |  |  | Orientation date has been sent
320 |  | Set up Shadowing schedules | open house, closing, buyer consult, showing houses, listing consult, inspection, transaction coordinator, appraisal |  | Operations
310 |  | Shadowing: Open House #1 |  |  | Administration
305 |  | Shadowing: Open House #2 |  |  | Administration
300 |  | Shadowing: Open House #3 |  |  | Administration
290 |  | Create Perfect Week Schedule |  |  | Operations | Perfect Week Sample for Agents |  |  | Perfect week has been created and reviewed with Team Leader
150 |  | Introduce to key people |  |  | Operations
140 |  | Showing Agent: Provide SA clipboard and forms |  |  | Administration
120 |  | Complete hands on training | Attend closing, attend open house, sit through initial buyer consult, MLS, CRM, phone systems, powerline |  | Operations |  |  |  | All training listed has been completed
100 |  | Confirm Required and recommended training | CRM, BAM, Role Playing, Scripts |  | Support |  |  |  | Agent has atended laid out training sessions
95 |  | Contacts new agent with orientation date | Get contact details from Team Leader |  | Support |  |  |  | New agent has confirmed orientation date
93 |  | Record username and passwords on password form | Check for any updates from Orientation |  | Support
90 |  | Confirm Orientation has been Completed | New agent will sign a sign in sheet at the end of orientation |  | Support | Agent Onboarding Sign In Sheet |  |  | Support has signed New Agent Orientation sign in sheet
90 |  | Support tells Team Leader of completed personnell file to move to private Drive | Send Team Leader email telling him file is ready to send from Master drive to private drive |  | Support
85 |  | Confirm Boot Camp dates and times | coordination between support, Agent Marketing, sales and Team Leader |  | Support |  |  |  | Bootcamp date has been confirmed
80 |  | Team Leader confirms with support that agent folder has been moved |  |  | Operations
75 |  | Support double checks the agent folder has been deleted from Master drive |  |  | Support | NEW AGENT
70 |  | Agent Marketing adds new agent bio to Agent Marketing Presentation books | 30 days after Orientation |  | Agent Marketing | Agent Marketing How to Change Presentation books |  |  | New pages have been added to presentation books
65 |  | Agent Marketing Orders Business Cards | After Orientation has been completed |  | Agent Marketing | Agent Marketing How to Order Business Cards |  |  | Business cards are in new agents possession
60 |  | Agent Marketing: Order wall plaque | Order plaque after 60 days of employment |  | Agent Marketing | How To's: Agent Marketing How to Order Wall Plaque |  |  | wall plaque is received in mail and email sent to Field Services to hang
55 |  | Agent Marketing: Notify Field Services to hang wall plaque |  |  | Agent Marketing |  |  |  | Confirmation email from Field Services of date task will be done
50 |  | Field Services sends confirmation email of when plaque will be hung | Reply to Agent Marketing email with date |  | Field Services |  |  |  | Agent Marketing has date
45 |  | Field Services to put up Agent wall plaque | Will get email from Agent Marketing that it has arrived |  | Field Services |  |  |  | Plaque is hung on wall

## Done Projects
Completed Projects
Importance | Sprint Date | Status | Project | Goal | Project Owner | Department | Done Date | Impediment
700
500
0

## Impediments
Impediments
Date Added | Date Removed | Assign To | Impediment | Notes

## Look Up Table
Look Up Table
Department | Project Owner | Status
Administration | Owner 1 | NS
Agent Marketing | Owner 2 | 100%
Operations | Owner 3 | 90%
Sales |  | 80%
Support |  | 70%
Transaction |  | 60%
Field Services |  | 50%
Lead Generation |  | 40%
CCC |  | 30%
20%
10%
5%
0%

## Instructions
Instructions
Please click on the link to be directed to a video we have created for your convenience. This video will give further assistance and instruction on how this spreadsheet works and what it is used for.
Agile Instruction Video
If you have any questions please email us at: help@workmansuccesssystems.com